## Sheet1
Sprint 1 | User Story | Task | Task assigned to | Estimated effort per task (hrs) | Actual effort per task (hrs) | Done | Notes
| As a User I want to be able to subscribe to a basic or a premium subscription | - Make controllers services and repositories for Team, User, Equipment, Field - Make entities for User and Team - Make endpoint to subscribe to basic subscription - Make endpoint to subscribe to premium subscription | - Jorn Dijk - Jorn Dijk - Jorn Dijk - Jason Miao | - 2 - 1 - 1 - 1 | - 2 - 1 - 1 - 1 | Yes
| As a User I want to be able to create an account | - Implement functionality to the controllers and services - Add tests | - Joppe Boerop - Kieran McAlpine | -1 -1 | -2 -2 | Yes
|  | - Add database connection logic | - Kieran McAlpine | -1 | -3 | Yes
| As a user I want to be able to login into my account | - Make entities for Reservation, FieldReservation, EquipmentReservation - Make entity for Field - Make tests for UserService - Make methods for login controller & repository & service | -Sorana Stan -Willem van de Sanden -Willem van de Sanden -Willem van de Sanden | -2 -1 -2 -2 | -3 -1 -2 -3 | Yes
Sprint 2
| Reorganise the template to fit the microservice architecture | - Make seperate modules for the microservices - Make a eureka server - Begin on the Team and Equipment microservice - Add seperate databases for the microservices | - Jorn Dijk and Jason Miao - Jorn Dijk and Jason Miao - Jorn Dijk - Jorn Dijk and Jason Miao | - 1 - 2 - 0.5 - 0.5 | - 5.5 - 5.5 - 1 - 1 | Yes | - Had to restructure the entire project as all the work done up to now were in one folder. The content inside was not partitioned into microservices. - Databases might not be set up entirely correct so need checking
|  | - Reconfigure database logic for new architecture | - Kieran McAlpine | -2 | -4 | No | - Databases working on a local copy of the repo, still needs to be made cleaner
Sprint 3